## ABC E-Commerce
| All modules have APIs as well |  |  | Done
Sr# | Module Name | Sub Modules | Team Members | Due Date | Completed Date | Dev. Status | QA Status
1 | UserManagement APIs | All User Management APIs | Ahsan Ejaz
| Categories |  | Ahsan Ejaz |  |  | completed
| Sub cattegories |  | Ahsan Ejaz |  |  | completed
| products by category |  | Ahsan Ejaz |  |  | completed
| products by sub-category |  | Ahsan Ejaz |  |  | completed
| add to cart |  | Ahsan Ejaz |  |  | completed
| order placement |  | Ahsan Ejaz |  |  | completed
| Re-Order |  | Ahsan Ejaz |  |  | inprogress
| Payment process |  |  |  |  | pending
| qr scan |  |  |  |  | pending
| profile |  | Ahsan Ejaz |  |  | completed
| Search product |  | Ahsan Ejaz |  |  | completed
| Web link |  | Ahsan Ejaz |  |  | completed
| Delete to cart |  | Ahsan Ejaz |  |  | completed
| Quantity increase/decrese |  | Ahsan Ejaz |  |  | completed
| Quantity Dyanmic |  | Ahsan Ejaz |  |  | completed
| Checkout |  | Ahsan Ejaz |  |  | completed
| get cart items |  | Ahsan Ejaz |  |  | completed